## BI
Project Tracking
No. | Created Date | Project Name | Module | Function | Description | Reported By | Risk | Solution | Responsed By | Due Date | Resolved Date | Closed Date | Reported To | Status | Pecentage
Updated: July 23, 2018

## CRM
Project Tracking
No. | Created Date | Project Name | Module | Function | Description | Reported By | Risk | Solution | Responsed By | Due Date | Resolved Date | Closed Date | Reported To | Status | Pecentage
Updated: July 23, 2018

## ITSD
Project Tracking
No. | Created Date | Project Name | Module | Function | Description | Reported By | Risk | Solution | Responsed By | Due Date | Resolved Date | Closed Date | Reported To | Status | Pecentage | Remark
1 |  | ITSD | Employee Register( Manager Dashboard ) | Employee Register ( UI ) |  | Mr. Sovannrath (Hean) |  |  | Mr. Sovannrath (Hean) |  |  |  | Mr. Kosal (Sy) | In Progress | 80% | Wait generate user to confirm email
2 |  | ITSD | IT Service Desk ( Manager Dashboard ) | Index ( UI ) Layout |  |  |  |  | Mr. Sovannrath (Hean) | [5 empty] | 100%
3 |  | ITSD | IT Service Desk ( Manager Dashboard ) | Create Incident Form |  |  |  |  | Mr. Sovannrath (Hean) | [5 empty] | 100%
4 | 31-7-2018 | ITSD | Incident Management ( Operator ) | List All incidents( UI ) with database | List Incident from database |  |  |  | Mr. Sovannrath (Hean) | [5 empty] | 90%
5 |  | ITSD | Employee Account ( Operator ) | Index | Fixing scroll employee profile |  |  |  | Mr. Sovannrath (Hean) | [5 empty] | 90%
6 | 2018-08-08 | ITSD | IT Service Desk ( Manager Dashboard ) | Create Incident & List All incidents by user |  | Mr. Sovannrath (Hean) |  |  | Mr. Sovannrath (Hean) | [5 empty] | 95%
7 | 14/08/2018 | ITSD | IT Service Desk ( Manager Dashboard ) |  |  | Mr. Sovannrath (Hean)
8 | 16/08/2018 | ITSD | IT Service Desk ( Operator Dashboard ) | Create Notification | Alert notifications after created incidents | Mr. Sovannrath (Hean) |  |  | Mr. Sovannrath (Hean) | [5 empty] | 30%
9 | 16/08/2018 | ITSD | Setup ( Operator Dashboard ) | Create, Update, User setup preference |  | Mr. Sovannrath (Hean) | [8 empty] | 100%
10 | 19/08/2018 | ITSD | Incident Management ( Operator ) | Create alert notification | Alert notification to CC Manager | [9 empty] | 90% | Waiting discussion
11 | 21/08/2018 | ITSD | Incident Management ( Operator ) | Display alert notification on system | Display notification on system
12 | 24/08/2018 | ITSD | IT Service Desk ( Manager ) | Create alert notification | Alert notification to Operator | Mr. Sovannrath (Hean) |  |  | Mr. Sovannrath (Hean)
13 | 25/08/2018 | ITSD | Meeting
14 | 27/08/2018 | ITSD | Employee Account ( Operator ) | Scroll employee profile | fix scroll employee profile and display Name of employee manager | Mr. Sovannrath (Hean) |  |  | Mr. Sovannrath (Hean) | [5 empty] | 100%
15 | 28/08/2018 | ITSD | Incident Management ( Operator ) | AttachFile | store original file name, preview attach file | Mr. Sovannrath (Hean) |  |  | Mr. Sovannrath (Hean) | [5 empty] | 100%
16 | 29/08/2018 | ITSD | Incident Management ( Operator ) | Index | fix view ID as Name and Details and view files | Mr. Sovannrath (Hean) |  |  | Mr. Sovannrath (Hean) | [5 empty] | 50%
17 | 30/08/2018 | ITSD | Incident Management ( Operator ) | Index | fix view ID as Name and Details and view files | Mr. Sovannrath (Hean) |  |  | Mr. Sovannrath (Hean) | [5 empty] | 80%
18 | 2018-03-09 | ITSD | Incident Management ( Operator ) | Index | fix view ID as Name and Details and view files | Mr. Sovannrath (Hean) |  |  | Mr. Sovannrath (Hean) | [5 empty] | 100%
19 | 2018-04-09 | ITSD | Incident Management ( Operator ) | edit incident | User can edit incident when status Open | Mr. Sovannrath (Hean) |  |  | Mr. Sovannrath (Hean) | [5 empty] | 100%
20 | 2018-05-09 | ITSD | Incident Management ( Operator ) | create and edit incident | Alert limit upload file size < 5MB | Mr. Sovannrath (Hean) |  |  | Mr. Sovannrath (Hean) | [5 empty] | 100%
| 2018-06-09 | ITSD | Operator | Alert notification | all notification 7 days ago | Mr. Sovannrath (Hean) |  |  | Mr. Sovannrath (Hean) | [5 empty] | 60%
| 19/9/2018 | ITSD | Operator+ Manager | Fix Grammar |  | Mr. Sovannrath (Hean) |  |  | Mr. Sovannrath (Hean)
Updated: July 23, 2018

## POS
Project Tracking
No. | Created Date | Project Name | Module | Function | Description | Reported By | Risk | Solution | Responsed By | Due Date | Resolved Date | Closed Date | Reported To | Status | Pecentage
Updated: July 23, 2018

## E-Leave
Project Tracking
No. | Created Date | Project Name | Module | Function | Description | Reported By | Risk | Solution | Responsed By | Due Date | Resolved Date | Closed Date | Reported To | Status | Pecentage
Updated: July 23, 2018

## Inventory
Project Tracking
No. | Created Date | Project Name | Module | Function | Description | Reported By | Risk | Solution | Responsed By | Due Date | Resolved Date | Closed Date | Reported To | Status | Pecentage
BIAS
Updated: July 23, 2018

## Digital Call Card
Project Tracking
No. | Created Date | Project Name | Module | Function | Description | Reported By | Risk | Solution | Responsed By | Due Date | Resolved Date | Closed Date | Reported To | Status | Pecentage
BIAS
Updated: July 23, 2018

## Mobile Delivery Tracking
Project Tracking
No. | Created Date | Project Name | Module | Function | Description | Reported By | Risk | Solution | Responsed By | Due Date | Resolved Date | Closed Date | Reported To | Status | Pecentage
BIAS
Updated: July 23, 2018

## fields (hidden)
Project Name | Reported By | Reported To | Status | Percentage
BIAS | Mr. Vuthy (Sin) | Mr. Kosal (Sy) | Open
CRMS | Mr. Channa (Pao) |  | In Progress
ITSD | Mr. Phana (Chhean) |  | Resolved
E-Leave | Mr. Sovannrath (Hean) |  | Closed
POS | Mr. Muth (Smai)
Inventory | Ms. Channary (Thay)
Digital Call Card
Mobile Delivery Tracking